## Sprint Overview
P2 Sprint Backlog — SDD Rev.A.6 §16.3 (Q4 2026, 6 weeks)
Sprint | Epic | Stories | Story Points | Goal | Risk | P1 dep | Phase
S5 (Wk 9-10) | Formations + Modes | P2-1, P2-2, P2-3, P2-8 | 20 | 9 formations operational, auto terrain switch | 9 formation visual validation, Hungarian compute time | P1-3, P1-14 | D
S6 (Wk 11-12) | Map + Lab Dev | P2-4, P2-5, P2-6, P2-7, P2-9 | 19 | Lab AHD camera + auto map prep + iptime config | AHD model availability, OSM PBF download size | P1-6, P1-7, P1-14 | D
S7 (Wk 13-14) | Tooling + Compliance | P2-10, P2-11, P2-12, P2-13, P2-14 | 29 | OTA, config mgmt, calibration, KPP automation | OTA partition complexity, KPP test variance | P1-3, P1-13, P1-15, P1-16 | D-E
Total | 3 Epics | 14 Stories | 68

## Stories Detail
All P2 Stories
Key | Summary | Sprint | Epic | Story Points | Priority | Components | SDD Ref | Blocked By | Labels | Status
P2-1 | 9 formations library (column, line, V, diamond, echelon, box, vee, free) | S5 (Wk 9-10) | EPIC-5 | 8 | High | mission | §7.2 | P1-3 | mission, P2, formation | To Do
P2-2 | Hungarian slot assignment (formation transition) | S5 (Wk 9-10) | EPIC-5 | 5 | High | swarm | §15.4 | P2-1 | swarm, P2, algorithm | To Do
P2-3 | Auto terrain switch (자동 종대 전환) | S5 (Wk 9-10) | EPIC-5 | 5 | High | mission | §7.5 | P2-1, P1-3 | mission, P2, auto | To Do
P2-8 | M4 assault mode (d=15m, 60°) | S5 (Wk 9-10) | EPIC-5 | 2 | High | mission | §7.8 | P1-14 | mission, P2, user-decision | To Do
P2-4 | AHD camera adapter (Lab dev mode) | S6 (Wk 11-12) | EPIC-6 | 5 | High | adapters | §2.2 | — | adapter, P2, user-decision | To Do
P2-5 | Hybrid static layer update (SLAM → OSM) | S6 (Wk 11-12) | EPIC-6 | 5 | High | mapping | §4.7.6 | P1-6, P1-7 | mapping, P2, algorithm | To Do
P2-6 | SRTM 30m DEM loader | S6 (Wk 11-12) | EPIC-6 | 3 | Medium | mapping | §10.5.1 | P1-6 | mapping, P2, terrain | To Do
P2-7 | mission_brief.sh — LTE map download automation | S6 (Wk 11-12) | EPIC-6 | 3 | Medium | scripts | §10.5.2 | P1-6, P2-6 | tooling, P2, shell | To Do
P2-9 | iptime mesh router auto-config | S6 (Wk 11-12) | EPIC-6 | 3 | Medium | scripts | §2.2 | — | network, P2, user-decision | To Do
P2-10 | OTA Update mechanism (A/B partition) | S7 (Wk 13-14) | EPIC-7 | 8 | High | scripts, core | §10.6.1 | — | infrastructure, P2, infra-x4 | To Do
P2-11 | Configuration Management (snapshot + rollback) | S7 (Wk 13-14) | EPIC-7 | 5 | High | core | §10.6.3 | P2-10, P1-16 | infrastructure, P2, infra-x5 | To Do
P2-12 | Calibration tools (IMU/camera/RTK) | S7 (Wk 13-14) | EPIC-7 | 8 | Medium | scripts | §16.3 | — | tooling, P2, infra-x8 | To Do
P2-13 | KPP 5종 자동 측정 (CI integration) | S7 (Wk 13-14) | EPIC-7 | 5 | High | tests, scripts | §5.6.5 | P1-3, P1-13, P1-15 | testing, P2, kpp, ci | To Do
P2-14 | AI 권한 분리 invariants 자동 검증 | S7 (Wk 13-14) | EPIC-7 | 3 | High | safety, core | §8 | P1-8, P1-16 | safety, P2, compliance | To Do

## Velocity
P2 Velocity Estimate
Total story points (P2): | 68
Sprints: | 3
Average SP/Sprint: | 22.6667
Avg duration (1 SP = 3 hrs): | 204 | hours
6 weeks × 40 hr/week: | 240 | hours per dev
Headroom: | 36 | hours buffer (~15%)
Top P2 Risks
ID | Risk | Probability | Mitigation
R1 | 9 formations may need visual tuning per real terrain | Medium | Phase D field trial validation; iterate per feedback
R2 | Hungarian assignment compute time at N=9 (>20 ms?) | Low | Profile + cache; fallback to greedy if needed
R3 | AHD camera model stock unpredictable | Medium | Validate 2-3 vendors; document drop-in alternative
R4 | OTA A/B partition disk size constraints (RK3588J 32 GB) | Medium | Compress; partition layout doc'd before Phase D
R5 | KPP test variance > 20% in CI environment | Medium | Run 5 iterations; report median + std dev
R6 | Calibration procedures need expert validation | Low | Seek input from Hanwha/LIG calibration teams

## P1 vs P2 Compare
P1 vs P2 Comparison
Metric | P1 (Q3 2026) | P2 (Q4 2026) | Ratio
Stories | 19 | 14 | 0.7x
Story Points | 107 | 68 | 64%
Sprints | 4 | 3 | 0.75x
Critical (⭐) | 3 | 0 | —
Duration (weeks) | 8 | 6 | 0.75x
Focus | KPP critical infra | Standard features + tooling
KPP impact | Direct (latency/reconfig) | Indirect (formation/calib)