## Sprint Overview
P1 Sprint Backlog — SDD Rev.A.6 §16.2 (Q3 2026, 8 weeks)
Sprint | Epic | Stories | Story Points | Critical (⭐) | KPP Impact | Goal | Risk
S1 (Wk 1-2) | Map + Swarm Core | P1-6, P1-7, P1-8, P1-1, P1-2 | 26 | 0 | Foundation | Cumulative mapping + 5-Tier escape ready | PBF rasterize complexity, Bayesian tuning
S2 (Wk 3-4) | Predictive + Hub UGV | P1-3, P1-4, P1-5, P1-13 | 34 | 0 | KPP 「150ms」 | 1-second prediction broadcast operational | Hybrid A* perf, election timing
S3 (Wk 5-6) | Operator Interface | P1-9, P1-10, P1-11, P1-12, P1-14 | 24 | 0 | User-facing | Android app fully integrated (BLE+WS+RPC) | BLE GATT impl, WS reliability
S4 (Wk 7-8) | Critical Infrastructure | P1-15, P1-16, P1-17, P1-18, P1-19 | 23 | 3 | Compliance + Safety | PTP+Audit+Health → field-deployable | PTP master single point, audit log perf
Total | 4 Epics | 19 Stories | 107 | 0

## Stories Detail
All P1 Stories
Key | Summary | Sprint | Epic | Story Points | Priority | Components | SDD Ref | Blocked By | Critical | Status
P1-6 | OSM PBF rasterizer (20 cm cell) | S1 (Wk 1-2) | EPIC-1 | 5 | Highest | mapping | §4.7.1, §10.5 | — |  | To Do
P1-7 | SLAM Persistent Layer with Bayesian update (α=0.95) | S1 (Wk 1-2) | EPIC-1 | 5 | Highest | mapping | §4.7.5 | P1-6 |  | To Do
P1-8 | Anomaly detection (OSM-SLAM mismatch threshold 0.7) | S1 (Wk 1-2) | EPIC-1 | 3 | Highest | mapping | §4.7.5, §15.6 | P1-7 |  | To Do
P1-1 | 5-Tier escape system (T0/T1.5/T1-T4) state machine | S1 (Wk 1-2) | EPIC-1 | 8 | Highest | swarm | §6.7 | — |  | To Do
P1-2 | Breadcrumb buffer (1.2 km, 1m or 0.5s sample) | S1 (Wk 1-2) | EPIC-1 | 5 | Highest | swarm | §6.7.1 | P1-1 |  | To Do
P1-3 | 1-second predictive broadcast (Hybrid A* lookahead) | S2 (Wk 3-4) | EPIC-2 | 13 | Highest | mission, swarm | §7.3 | P1-13 |  | To Do
P1-4 | Leader rollback policy (≥50% follower struggling → retreat + replan) | S2 (Wk 3-4) | EPIC-2 | 5 | Highest | mission | §7.6 | P1-1, P1-3 |  | To Do
P1-5 | Hub UGV adapter (SLAM fusion + comm gateway + leader takeover) | S2 (Wk 3-4) | EPIC-2 | 8 | Highest | adapters | §2.2, §6.5 | P1-7 |  | To Do
P1-13 | Modified Raft + DDS Liveliness QoS | S2 (Wk 3-4) | EPIC-2 | 8 | Highest | swarm | §6, §6.5 | — |  | To Do
P1-9 | BLE GATT API (UUID 0xFF00-0xFF05) | S3 (Wk 5-6) | EPIC-3 | 8 | Highest | control | §15.2 | — |  | To Do
P1-10 | WebSocket JSON-RPC API (11 method) | S3 (Wk 5-6) | EPIC-3 | 8 | Highest | control | §15.3 | — |  | To Do
P1-11 | Telemetry 30 Hz format (robots[] + tier color codes) | S3 (Wk 5-6) | EPIC-3 | 3 | Highest | control | §15.5 | P1-10, P1-1 |  | To Do
P1-12 | Anomaly Event push format with image_url + severity | S3 (Wk 5-6) | EPIC-3 | 2 | Highest | control, comm | §15.6 | P1-10, P1-8 |  | To Do
P1-14 | Operational mode single rule (Test 3m / Move 5m / Assault 15m) | S3 (Wk 5-6) | EPIC-3 | 3 | Highest | mission | §7.1, §15.7 | P1-10 |  | To Do
P1-15 | Time Synchronization (PTP / GNSS PPS) | S4 (Wk 7-8) | EPIC-4 | 5 | Highest | core | §5.8 | — | ⭐ | To Do
P1-16 | Audit Log (hash-chained jsonl) | S4 (Wk 7-8) | EPIC-4 | 5 | Highest | core, safety | §9.7 | — | ⭐ | To Do
P1-17 | Health Monitoring + Degraded Mode FSM | S4 (Wk 7-8) | EPIC-4 | 8 | Highest | safety | §9.6 | P1-15 | ⭐ | To Do
P1-18 | Geofence violation detection (E3 event) | S4 (Wk 7-8) | EPIC-4 | 3 | Highest | safety | §9.3 | — |  | To Do
P1-19 | Battery 20% → automatic RTH trigger | S4 (Wk 7-8) | EPIC-4 | 2 | Highest | safety, mission | §8 | P1-17 |  | To Do

## Velocity
Velocity Estimate
Total story points (P1): | 107
Sprints: | 4
Average SP/Sprint: | 26.75
Avg duration (1 SP = 3 hrs): | 321 | hours
8 weeks × 40 hr/week: | 320 | hours per dev
Headroom check: | -1 | hours buffer
Top Risks
ID | Risk | Probability | Mitigation
R1 | PTP master (Hub UGV) single point of failure | Medium | Quorum-based fallback consensus per §5.8.3
R2 | 1-sec predictive Hybrid A* may not meet 100ms compute budget | High | Use cached path, only re-plan when significant divergence
R3 | BLE GATT implementation cross-platform issues | Medium | Use BleSim TCP simulator for tests, hardware in Phase C
R4 | 5-Tier hysteresis chattering in marginal scenarios | Medium | Aggressive testing in Gazebo with edge cases
R5 | Audit log overhead may exceed 5 ms per write | Low | Async batch writes, separate disk partition